## Slide 1: Software Project Management
Jing Zhang Ph.D.

## Slide 2: Activity planning
Objectives:
Produce an activity plan for a project
Estimate the overall duration of a project
Create a critical path and a precedence network for a project

## Slide 3: Introduction
A detailed plan for the project must include a schedule indicating the start and completion times for each activity. This will enable us to:
  Ensure that resources will be available when required;
  Avoid different activities competing for the same resource at the same time;
  Produce a detailed schedule showing which staff carry out each activity;
  Produce a detailed plan against which actual achievement may be measured;
  Produce a timed cash flow forecast;
  Re-plan the project during its life to correct drift from the target.

## Slide 4: Projects and activities-Definition
A project is composed of a number of interrelated activities.
A project may start when at least one of its activities is ready to start;
A project will be completed when all of the activities it encompasses have been completed;
An activity must have a clearly defined start and a clearly define end-point;
Resource requirement must be forecastable and at a constant level throughout the duration of the activity;
The duration of an activity must be forecastable;
Some activities might require that others are completed before they can begin (known as precedence requirements) .

## Slide 5: Network planning models
These project scheduling techniques model the project’s activities and their relationships as a network. In the network, time flows from left to right. These techniques were originally developed in the 1950s – known as CPM (Critical Path Method) and PERT (Program Evaluation Review Technique)
Two types of networks
  Activity-on-node (precedence networks)
  Activity-on-arrow
CPM was developed by the Du Pont Chemical Company in 1958, claiming that it had saved them $1 million in its first year of use.
Code
Data take-on
Program test
Install
Program test
Install
Code
Data take-on

## Slide 6: Formulating a network model
Constructing well-formed precedence networks
  A project network should have only one start node.
  A project network should have only one end node.
  A node has duration
  Links normally have no duration. Links represent the relationships between activities.
  Precedents are the immediate preceding activities. We do not speak of ‘Code’ and ‘Data take-on’ as precedents of ‘Install’.
  Time moves from left to right.
  A network may not contain loops.
  A network should not contain dangle.

## Slide 7: Examples
Code Program
Correct
errors
Test Program
Release Program
Diagnose
errors
Code Program
Writer User
manual
Test Program
Install Program
Design Program
Code Program
Correct
Errors 1
Test Program 1
Release Program
Diagnose
Errors 1
Correct
Errors n
Test Program n
Diagnose
Errors n
Code Program
Writer User
manual
Test Program
Install Program
Design Program
Sign-off
Which attribute of the activity does the case violate?

## Slide 8: Representing lagged activities
Where activities can occur in parallel with a time lag between them, we represent the lag with a duration on the linking arrow.
The above figure indicates that documenting amendments can start one day after the start of prototype testing and will be completed two days after prototype testing is completed.
Test prototype
Document amendments
Revise specification
Build prototype
1
2

## Slide 9: Labeling conventions
There are a number of different conventions that have been adopted for entering information on an activity-on-node network.
Earliest start | duration | Earliest completion
Description of the activity |  | 
Latest start | float | Latest completion

## Slide 10: Time dimension
Example
Activity | Duration (week) | Precedents
A. Hardware selection | 6 | 
B. System configuration | 4 | 
C. Install hardware | 3 | A
D. Data migration | 4 | B
E. Draft office procedures | 3 | B
F. Recruit staff | 10 | 
G. User training | 3 | E, F
H. Install and test system | 2 | C, D

## Slide 11
 | 6 weeks | 
A. Hardware selection |  | 
 | 4 weeks | 
D. Data migration |  | 
 | 4 weeks | 
B. Software configuration |  | 
 | 2 weeks | 
H. Install and test |  | 
 | 10 weeks | 
F. Recruit staff |  | 
 | 3 weeks | 
E. Draft office procedures |  | 
 | 3 weeks | 
G. User training |  | 
 | 3 weeks | 
C. Install hardware |  | 
The precedence network for the example project

## Slide 12
The forward pass
  Calculate the earliest dates on which each activity may be started and completed
 | 6 weeks | 
A. Hardware selection |  | 
 | 4 weeks | 
D. Data migration |  | 
 | 4 weeks | 
B. Software configuration |  | 
 | 2 weeks | 
H. Install and test |  | 
 | 10 weeks | 
F. Recruit staff |  | 
 | 3 weeks | 
E. Draft office procedures |  | 
 | 3 weeks | 
G. User training |  | 
 | 3 weeks | 
C. Install hardware |  | 
0
0
0
4
6
10
4
6
4
8
9
7
9
10
11
13

## Slide 13
The backward pass
  Calculate the latest dates at which each activity may be started and finished without delaying the end date of the project.
 | 6 weeks | 
A. Hardware selection |  | 
 | 4 weeks | 
D. Data migration |  | 
 | 4 weeks | 
B. Software configuration |  | 
 | 2 weeks | 
H. Install and test |  | 
 | 10 weeks | 
F. Recruit staff |  | 
 | 3 weeks | 
E. Draft office procedures |  | 
 | 3 weeks | 
G. User training |  | 
 | 3 weeks | 
C. Install hardware |  | 
0
0
0
4
6
10
4
6
4
8
9
7
9
10
11
13
13
13
11
10
11
10
11
7
7
8
7
10
8
3
0
2

## Slide 14
Identifying the critical path
  There will be at least one path through the network that defines the duration of the project. This is known as the critical path.
  Critical activity: float = 0 (latest completion – earliest completion)
  There will be at least one path through the network joining those critical activities.
 | 6 weeks | 
A. Hardware selection |  | 
 | 4 weeks | 
D. Data migration |  | 
 | 4 weeks | 
B. Software configuration |  | 
 | 2 weeks | 
H. Install and test |  | 
 | 10 weeks | 
F. Recruit staff |  | 
 | 3 weeks | 
E. Draft office procedures |  | 
 | 3 weeks | 
G. User training |  | 
 | 3 weeks | 
C. Install hardware |  | 
0
0
0
4
6
10
4
6
4
8
9
7
9
10
11
13
13
13
11
10
11
10
11
7
7
8
7
10
8
3
0
2
3
3
2
3
0
2
2
0

## Slide 15: Conclusion
We can use the critical path method and precedence networks to obtain an ideal activity plan.
This plan tell us the order in which we should execute activities and the earliest and latest we can start and finish them.
These techniques help us to identify which activities are critical to meeting a target of completion date.

## Slide 16: Homework
6.18 Further exercise
  4